## Sheet1
Task | Date | Cael Time (hours) | Matt Time (hours) | Description | Cael Total Time | Matt Total Time
Team Contract Drafting | 2025-09-12 | 1 | 1 | We had collectively discussed the team contract and the possible advisors for the overall project | 8.5 | 10
Advisor Discussion | 2025-09-16 | 0 | 0.25 | Matt met with professor Abuaitah where he confirmed his committment to be our capstone advisor.
Design Diagrams and User Stories | 2025-09-19 | 1 | 1 | Began project design diagrams and finished user stories, project goals, and diagram convention sections.
Task List | 2025-09-28 | 0.75 | 0.75 | Completed the task list assignment consisting of enumerating the various tasks we intend to complete to satisfy project requirements.
Milestone List | 2025-10-03 | 1.5 | 1.5 | Completed milestone list including deliverables, timeline, and effor t percentages.
Constraints Essay | 2025-10-10 | 0.75 | 0.75 | Completed constraints essay task, enumerating various constraints that our project's development faces.
Base Unity Project | 2025-10-24 | 0 | 1.25 | Pushed a Unity project to our Git repo that contians the base components to build upon for our project
Fall Presentation | 2025-10-24 | 1.5 | 1.5 | Created slide deck and presentation
Final Design Report | 2025-11-21 | 2 | 2 | Formatted the Git repository into one acceptable for Assignment 10 by adding links and the remaining assignments.